## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
That User Story | Code Things…
Select games that I own/ enjoy | UI for selection, searchable, possibily sortable by genres | 6 | 6 | 6 | 6 | 6
| Game object, that holds game information | 3 | 1 | 1 | 0 | 0
| Genre enum | 2 | 1 | 1 | 0 | 0
| No database as of now so prexisting local list of games (import game library from csv) | 4 | 2 | 1 | 0 | 0
| User Validation(might not need since we are the ones uploading games) | 4 | 4 | 0 | 0 | 0
| Testing model/ viewmodel | 2 | 2 | 2
Find recommended/ suggested games | UI for recommendation engine, swipe left or right | 8 | 8 | 2 | 0 | 0
| Mystiverse page | 6 | 6 | 6 | 6 | 6
| UI element for each recommended game | 4 | 4 | 0 | 0 | 0
| Build game Recommendation engine | 6 | 6 | 2 | 0 | 0
| Functionality to save, liked/ dislikes games and genres, based on user's choices | 4 | 4 | 2 | 0 | 0
| Testing model/ viewmodel | 2 | 2 | 1 | 0
Access and view game library | UI for game library, show user's owned games | 6 | 6 | 3 | 0 | 0
| UI to display details from game, use image here | 6 | 6 | 5
| UI for ability to select new game user owns | 4 | 4 | 4
| Library object, which holds maybe a user and then pull the list of games related to that user | 4 | 4 | 2 | 0 | 0
| Testing model/ viewmodel | 4 | 4 | 4 | 0 | 0
Create a profile | UI for creating a profile, needs to navigate to UI selection of games | 6 | 6 | 1 | 0 | 0
| UI for basic profile page | 6 | 6 | 1 | 0 | 0
| UI allowing user to edit preferences, undo likes, dislikes | 6 | 6 | 6 | 0 | 0
| User/ Profile object, holds user information, list of own games, likes and dislikes | 4 | 1 | 1 | 0 | 0
| Testing model/ viewmodel | 4 | 4 | 4 | 0 | 0
| Create ActiveUser, storing current user | 2 | 2 | 1 | 0 | 0
| Create Profile Attributes to hold more user info | 3 | 3 | 1 | 0 | 0
| Designing Profile SubPages( Edit Preferences, Edit Profile, Settings Profile) | 10 | 6 | 4 | 2 | 0
| Creating subPages viewmodel | 6 | 3 | 2 | 1 | 0
| Testing viewmodel of subpages | 10 | 7 | 4 | 3 | 0
| Estimate Totals | 132 | 114 | 67 | 18 | 12
Jeffrey