## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
That User Story | Code Things… | 100 | 75 | 50 | 25 | 0
Library refactor and redesigning |  | 3 | 3 | 2 | 1
Implement ability select owned games on library page |  | 3 | 3 | 3 | 0
Implement ability to select different games on library page (owned, played, liked, disliked) |  | 3 | 3 | 2 | 0
Remove games on library page (liked, disliked, owned) |  | 3 | 3 | 3 | 3
Implement game details displayed on click |  | 3 | 3 | 0 | 0
Implement ability to show different library of games (owned, played, liked, disliked) |  | 3 | 3 | 2 | 0
Test above |  | 3 | 3 | 3 | 2
Mystiverse refactor and redesign |  | 3 | 3 | 2 | 0
Skip button for recommendation views |  | 3 | 3 | 1 | 0
Custom seed info for recommendation, user can input |  | 3 | 3 | 2 | 0
Implement seeded recommendation engine |  | 3 | 3 | 3 | 0
Implement seeded recommendation preferences pages |  | 3 | 3 | 2 | 0
Test above |  | 3 | 3 | 3 | 3
Implement base sever project |  | 3 | 2 | 0 | 0
integrate login with server |  | 5 | 4 | 2 | 0
login java model server implementation |  | 6 | 4 | 2 | 0
login credential/ credentialManager python model |  | 3 | 1 | 1 | 0
Implement requests |  | 6 | 4 | 3 | 0
Test above |  | 8 | 8 | 8 | 8
Redesign selection page |  | 6 | 6 | 6 | 0
Library page becomes landing page if not first time login, if first time go to selection page |  | 3 | 3 | 3 | 0
Implement static Image loader |  | 3 | 3 | 0 | 0
integrate library with server |  | 3 | 3 | 0 | 0
library java model server implementation |  | 3 | 3 | 0 | 0
library python model |  | 3 | 3 | 0 | 0
server reads in game database on startup |  | 3 | 3 | 0 | 0
Implement requests |  | 3 | 3 | 0 | 0
Test above |  | 3 | 3 | 3 | 3
integrate mystiverse with server |  | 3 | 3 | 2 | 2
recommendation engine java model server implementation |  | 3 | 3 | 2 | 2
recommendation engine python model |  | 3 | 3 | 2 | 2
Implement requests |  | 3 | 3 | 3 | 3
Test above |  | 3 | 3 | 3 | 3
| Estimate Totals | 215 | 182 | 118 | 57 | 0
Dillion
Daniel
Jeffrey
Thomas